## Sheet1
Date/Location | Activity | Progress (TODO) | Members
Tuesday (2/19/19) 6:00 PM - 8:00 PM | Outlined decoder alogrithm | Fix chosen project 1 for incorrect hexadecimal | Richard, Syed
Wednesday (2/20/19) 6:00 PM - 9:15 PM | Added 1 function for two's comp, more instruction conversions for branches, finished test case 1 | Add instruction conversion for sub, and | Richard, Syed
Friday (2/22/19) 6:00 PM - 2:00 AM | Finished test case 2, do more instruction conversion (sll and srl) | Fix srl functionality | Richard, Syed
Satuday (2/23/19) 12:00PM - 2:00 PM | Understanding the program/ Looking over case 4 | Fixed offset on Lw and sw instructions. Fixing other potential issues | Rami
Sunday (2/24/19) 4:00 PM - 5:00 PM | Fixed srl functionality | Finish test case 3, make a printing function | Richard
Monday (2/25/19) 6:00 PM - 12:00 PM | Finished test case 3, implemented printing function to output file, added sw and lw functionality | Finish up test case 4 | Richard, Syed
Tuesday (2/26/19) 1:30 PM - 2:30 PM | Finished test case 4, accomodated lw and sw for output file | Test the decoder using Project 1 code | Richard
Tuesday (2/26/19) 6:00 PM - 3:00 AM | Fixed debugging issues, ran PRPG program successfully | Test the decoder using Project 1 code part 2 | Richard
Tuesday (2/26/19) 6:00 PM - 3:00 AM | Fixed sll, slt functionality | Test the decoder for the hamming distances | Syed
Wednesday (2/27/19) 6:00 PM - 11:00 PM | Fixed the 32bit and 16 bit two's Complement | Test the decoder for the hamming distances | Syed
Thursday (2/27/19) 1:00 PM - 8:00 PM | Made sure it runs for all the given test cases for PRGP | Test cases | Syed, Richard
Thursday (2/27/19) 8:00 PM - 10:00 PM | Made up test cases 1B and 2B |  | Syed